## V1
Project Development and Completion Tracker
Porject ID: SY2003
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption:An Android and iOS application for promoting sustainable and eco-friendly products, supporting startups, rural communities, and tribal artisans. The app focuses on providing a seamless marketplace experience and promoting environmental consciousness.
| Name of Team member | Designation
Project Architech Team Members | Shreyash Nimbhorkar | Front-end & Back-end Developer
| Kartik Nair | UX Designer
Epic: | As a customer, I want to browse and purchase eco-friendly products while promoting sustainability and supporting small businesses.
Story 1: | As a customer, I want to register/login securely so that I can personalize my experience.
Story 2: | As a customer, I want to browse products by categories and price range. As a customer, I want to know the environmental impact of each product I purchase
Story 3: | As a seller, I want to register my business to list products and track sales.
Task1: | Design user registration and login system with database connectivity.
Task2: | Develop product listing layout and integrate it with a database of sustainable products
Task3: | Implement a cart and checkout feature with secure payment integration.
Task4: | Build an analytics page to display environmental impact metrics of purchased products.
Task5: | Develop a seller portal for business registration and product uploads.
Acceptance Criteria:
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Design User Registration and Login System | Layout Design | Complete | Shreyash,kartik | 2024-09-03 | 2024-09-12 | 2024-09-03 |  | 100% | Not Started | Medium
|  | Database configuration | Complete | Shreyash,kartik | 2024-09-03 | 2024-09-12 |  |  | 100%
| Design login page layout. | Layout Design | complete | Shreyash,kartik | 2022-02-03 | 2024-10-12 | 2022-02-04 |  | 100% | In Progress | Low
|  | Database design and connectivity | In Progress | Shreyash,kartik | 2024-10-20 | 2024-10-12 | 2024-10-04 |  | 50%
|  | Database desing and connectivity | In Progress | Shreyash,kartik | 2021-10-20 | 2022-02-12 | 2024-10-04 |  | 60%
| Integration of all Layouts |  | in Progress | Shreyash,kartik | 2024-09-23 | 2024-09-12 |  |  | 40%
Sprint 1 | Develop Product Listing Layout | Layout Design , Database configuration | complete | Shreyash,kartik | 2024-10-20 | 2024-11-19 |  |  | 100% | On Hold
| Database Connectivity for Product Listings | Database configuration | In Progress | [5 empty] | 60% | Overdue
| Develop Seller Portal | Layout Design UI Design for Sellers | Complete | Shreyash |  |  |  |  | 100%
User Registration and Login
Input fields with validations (name, email, password).
Secure login with error handling.
Product Listing
User-friendly layout with filters by category and price.
Dynamic product display from the database.

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2